## Instructions
ATL - BIM Standards ¦ LOD Definitions
Updated: | 2025-07-01
TAB> | DELIVERABLES | List of all deliverables for a project ( models - documents - drawings - reports - etc )
| LOD DEFINITION | Level of Detail (LOD) and Level of Information (LOI) - Definition
| UNIFORMAT CODE | How to obtain the Unifomat Code to be incorporated in the model (by component)
| PARAMETERS | List of Mandatory Parameters to add in the model by Stage
| NAMING CODES | Naming Convention Structure Definition
STEP 1 | DELIVERABLES
Purpose: This tab lists all the deliverables for a project, including models, documents, drawings, reports, etc. How to Use: Add each deliverable item in a new row. Include all relevant information related to each deliverable, such as the file name, description, due date, and status.
STEP 2 | LOD DEFINITION
Purpose: This tab defines the Level of Detail (LOD) and Level of Information (LOI) for the project. How to Use: Refer to this tab to understand the required LOD and LOI for different stages of the project. Ensure that the models and documents meet the specified LOD and LOI requirements.
STEP 3 | UNIFORMAT CODE
Purpose: This tab provides information on how to obtain the Uniformat Code to be incorporated in the model by component. How to Use: Use the guidelines provided to assign the correct Uniformat Code to each component in the model. Ensure that all components are coded accurately as per the instructions.
STEP 4 | PARAMETERS
Purpose: This tab lists the mandatory parameters that need to be added to the model by stage. How to Use: Review the list of parameters and ensure that they are included in the model at the appropriate stage. Verify that all mandatory parameters are correctly populated.
STEP 5 | NAMING CODES
Purpose: This tab defines the naming convention structure for the project. How to Use: Follow the naming convention guidelines to name all files, components, and documents consistently. Ensure that the naming codes are applied correctly to maintain uniformity across the project.
STEP 6
STEP 7
STEP 8

## Deliverables
ATL ¦ Deliverables List
File Name | ProjectID | Originator | Level | Type | Role | Number | Use | LOD | Format | Location | Author | Submission Date | Review Status
3D MODEL
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | Atlanta Airport BIM | 00/00/00 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | SharePoint | WSP | 00/00/01 | RE-SUBMIT
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | Atlanta Airport BIM | 00/00/02 | ACEPTED
F0000000-ATL-XX-M3-NV-01 | F0000000 | ATL | XX | M3 | NV | 01 | 3D MODEL | 300 | RVT | Drive | WSP | 00/00/03 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | XXX | 00/00/04 | ACEPTED w/COMMENTS
F0000000-ATL-XX-M3-ME-05 | F0000000 | ATL | XX | M3 | ME | 05 | 3D MODEL | 300 | RVT | ACC | WSP | 00/00/05 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | Atlanta Airport BIM | 00/00/06 | RE-SUBMIT
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | WSP | 00/00/07 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | WSP | 00/00/08 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | RVT | ACC | WSP | 00/00/09 | ACEPTED
3D COORDINATION
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | NWC | ACC | WSP | 00/00/07 | RE-SUBMIT
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | NWC | ACC | WSP | 00/00/07 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | NWF | ACC | WSP | 00/00/07 | ACEPTED w/COMMENTS
F0000000-ATL-XX-M3-NV-01 | F0000000 | ATL | XX | M3 | NV | 01 | 3D MODEL | 300 | NWF | ACC | WSP | 00/00/07 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | NWF | ACC | WSP | 00/00/07 | ACEPTED
F0000000-ATL-XX-M3-AR-01 | F0000000 | ATL | XX | M3 | AR | 01 | 3D MODEL | 300 | NWF | ACC | WSP | 00/00/07 | ACEPTED
2D DRAWINGS
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/07 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/01 | RE-SUBMIT
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/02 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/03 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/04 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/05 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/06 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/07 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/08 | ACEPTED
F0000000-ATL-XX-M2-AR-01 | F0000000 | ATL | XX | M2 | AR | 01 | 2D DRAWING | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/09 | ACEPTED
DOCUMENTS
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | DOCUMENT | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/09 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | SCHEDULE | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/10 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | SCHEDULE | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/11 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | DOCUMENT | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/12 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | REPORT | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/13 | ACEPTED
F0000000-WSP-XX-DC-GN-01 | F0000000 | WSP | XX | DC | GN | 01 | DOCUMENT | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/14 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | TEMPLATE | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/15 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | EXCHANGE | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/16 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | SCHEDULE | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/17 | ACEPTED
F0000000-ATL-XX-DC-GN-01 | F0000000 | ATL | XX | DC | GN | 01 | DOCUMENT | N/A | PDF | SharePoint | Atlanta Airport BIM | 00/00/18 | ACEPTED

## LOD Definition
ATL ¦ LOD Definitions
CONCEPTUAL DESIGN | PRELIMINARY DESIGN | BASIS OF DESIGN | DESIGN FOR CONSTRUCTION | AS CONSTRUCTED
LOD 100 | LOD 200 | LOD300 | LOD400 | LOD500
APROXIMATE GEOMETRY |  | PRECISE GEOMETRY |  | PLUS CONNECTIONS
NO DATA NEEDED |  | SOME DATA ADDED TO COMPONENTS |  | FULL SET DATA
REPRESENTATION ¦ SYMBOL | GEOMETRY | SPECIFICATION AND MATERIALS | SHAPE&SIZE ¦ MANUFACTURER | CONNECTIONS ¦ FULL SPEC
LOD 100 – Conceptual Definition: Model elements are represented symbolically. Description: At LOD 100, the model focuses on conveying basic concepts and ideas. Elements are represented in a schematic or symbolic manner, without precise geometric accuracy. Information: Parameters may be included, but not based on detailed design. Purpose: This level is suitable for early-stage design, feasibility studies, and high-level planning. It helps to visualize the overall project scope and explore different design options. Example: A building might be represented as a simple box with an approximate area. | LOD 200 – Approximate Geometry Definition: Elements are represented with generalized geometry and location. Description: LOD 200 introduces approximate geometry and location for model elements. While not precise, the elements begin to resemble their actual shape and position within the building. Information: Quantities, size, shape, orientation, and location are approximate. This level provides a better understanding of the spatial relationships between elements. Purpose: LOD 200 is used for schematic design and design development. It allows for more accurate cost estimation and preliminary coordination. Example: Walls are represented with approximate thickness and height, and windows are placed in their general locations. | LOD 300 – Precise Geometry Definition: Model elements are graphically represented with accurate geometry and location. Description: At LOD 300, model elements are represented with precise geometry and accurate location. This level of detail allows for detailed design coordination and analysis. Information: The model includes accurate dimensions, shapes, and positions of elements. Purpose: LOD 300 is suitable for construction documentation, detailed design coordination, and quantity take-off. It provides a reliable basis for generating accurate cost estimates and schedules. Example: Walls, windows, and doors are modeled with their exact dimensions and placed in their precise locations. | LOD 350/400 – Detailed Connections Definition: Includes LOD 300 plus interfaces with other building systems (e.g., supports, connections, clearances). Description: LOD 350 builds upon LOD 300 by adding detailed information about the interfaces and connections between building systems. Information: This includes supports, connections, clearances, and other elements necessary for coordinating different trades. Purpose: LOD 350 is used for clash detection, coordination of MEP systems, and ensuring constructability. It helps to identify and resolve potential conflicts before construction begins. Example: HVAC ducts are modeled with their connections to diffusers and equipment, and structural supports are shown in detail. | LOD 500 – As-Built Definition: Reflects the actual built condition. Description: LOD 500 represents the as-built condition of the project. Information: It includes verified field data and reflects any changes made during construction. Purpose: LOD 500 is used for operations and maintenance, facilities management, and future renovations. It provides an accurate record of the building's physical characteristics and systems. Example: The model reflects the actual locations of pipes, ducts, and electrical conduits, as well as any changes made during construction

## UNIFORMAT CODE
ATL ¦ Uniformat Code
Steps to check and add the Uniformat Code
Open the Spreadsheet> ATL-TP-EXC-AssetDefinition_2025-v1.xlsx
1 | Stay in the Navigation Menu
2 | Select Level 1 of definition
3 | Select Level 2 of definition
4 | Select Level 3 of definition
5 | You can find the element list at the bottom and select the correct Uniformat Code to fill the Parameter in your model

## PARAMETERS
ATL ¦ Parameters
Parameter Name | Data Set | LOD | Description | Category | Data Type | Example | Source
Standard Parameters
Room Name | Location | 200 | Name of the room | Name | Text | Mechanical Room | Revit Parameter
Room Number | Location | 200 | Number of the room | Name | Number |  | Revit Parameter
Width | Object | 300 | Width of the element | Dimension | Number | 20 | Revit Parameter
Depth | Object | 300 | Depth of the element | Dimension | Number | 150 | Revit Parameter
Height | Object | 300 | Height of the element | Dimension | Number | 13 | Revit Parameter
Material | Object | 300 | Material of the element | Material | Material | Aluminum | Revit Parameter
Detailed Parameters
Uniformat |  | 300 | Unique identifier - source of the true system of record (EAM) | Code | Text | 123456, P12345 | Assigned by user
ATL-Asset Item |  | 400 | This element is an Asset | General | Yes/No |  | Assigned by user
ATL-Equipment Type/Class |  | 400 | Specific type of asset that is unique for each individual asset class (see detailed asset description for values) | Data | Text | Wet Pipe - Dry Pipe - Halon, CO2 | Assigned by user
ATL-Asset Tag ID |  | 400 | Based on Asset Tagging Strategy | Data | Text | TBD | Filled by List
ATL-Asset Description |  | 400 | Description to identify the asset | Data | Text | PUMP 01, SERVICES ELEVATOR | Filled by List
ATL-Asset Physical Location |  | 400 | Based on the Asset Physical Location Identification Strategy | Data | Text | TBD | Revit Parameter
ATL-Manufacturer |  | 400 | Manufacturer name for the asset | Data | Text | Sulzer, Inc | Assigned by user
ATL-Serial Number |  | 400 | Serial number for asset if any | Data | Text | S/N: 332490-23KJ-KKS | Assigned by user
ATL-Model |  | 400 | Model for asset if any | Data | Text | Model: 1500 Series | Assigned by user
ATL-O&M Manual |  | 400 | Document file name as provided at time of turnover | Data | Text | PUMP_01_SVCMNL.pdf | Assigned by user
ATL-Manufacturer Warranty Document |  | 400 | Document file name as provided at time of turnover | Data | Text | PUMP_01_WARR_MANU.pdf | Assigned by user
ATL-Installation Warranty Document |  | 400 | Document file name as provided at time of turnover | Data | Text | PUMP_01_WARR_INST.pdf | Assigned by user
ATL-Installation/Construction Date |  | 400 | Date of installation or construction | Data | Date | 40494 | Assigned by user
ATL-Substantial Completion Date |  | 400 | Date of substantial completion | Data | Date | 40494 | Assigned by user
ATL-Refurbished Date |  | 400 | Date of asset refurbishment | Data | Date | 40494 | Assigned by user
ATL-Manufacturer Warranty Start Date |  | 400 | Warranty Start Date | Data | Date | 45242 | Assigned by user
ATL-Manufacturer Warranty End Date |  | 400 | Warranty End Date | Data | Date | 45973 | Assigned by user
ATL-Installation Warranty Start Date |  | 400 | Warranty Start Date for Installer | Data | Date | 45973 | Assigned by user
ATL-Installation Warranty End Date |  | 400 | Warranty End Date for Installer | Data | Date | 45973 | Assigned by user
ATL-Design Life |  | 400 | Asset OEM expected life of service in years | Data | Text | 10 | Assigned by user
ATL-OEM/Construction Cost |  | 400 | OEM or construction cost | Data | $ Currency | US$ 20,000.00 | Assigned by user
ATL-Replacement Cost |  | 400 | Cost to replace the whole asset per original or new specifications at time of turn over | Data | $ Currency | US$ 20,000.00 | Assigned by user
ATL-Refurbished Cost |  | 400 | Cost of overhauling the asset, as per OEM/Builder/Design Specifications at time of turn over | Data | $ Currency | US$ 20,000.00 | Assigned by user
ATL-Estimated O&M Cost |  | 400 | Projected annual O&M costs at time of turn over | Data | $ Currency | US$ 20,000.00 | Assigned by user

## NAMING CODES
ATL ¦ Naming Codes
ProjectID | Originator | Originator | Level | Level | Type | Type | Role | Role | Number | Format | Location | Author | Review Status | LOD | Category | Type | Source | Zone | Level | Room | Door
F0000000 | ATL | Atlanta Airport | XX | no level | D1 | 2D DRAWING | AR | Architecture | 01 | DOC | Drive | Atlanta Airport BIM | ACEPTED | 100 | Dimension | Number | Assigned by user | MW | 7 | F5 | A
F0000000 | WSP | WSP company | 01 | level 1 | M2 | 2D MODEL | CV | Civil | 02 | DWG | ACC | WSP | RE-SUBMIT | 200 | Name | Text | Revit Parameter | MA | 6 | B1 | B
F0000000 | XXX | Add 3 letters | 02 | level 2 | M3 | 3D MODEL | SU | Survey | 03 | EXE | SharePoint | XXX | ACEPTED w/COMMENTS | 300 | General | Material | Filled by List | ME | 5 | M1 | C
F0000000 | XXX |  | 03 | level 3 | M4 | 4D SIMULATION | EL | Electrical | 04 | MAIL |  |  |  | 400 | Material | Yes/No |  | MN | 4 | S1 | D
F0000000 | XXX |  | 04 | level 4 | DC | DOCUMENT | FP | Fire Protection | 05 | NWC |  |  |  | 500 | Code | Date |  | MS | 3 | D3 | E
F0000000 | XXX |  | 05 | level 5 | S1 | SCHEDULE | GE | Geotechnical | 06 | NWF |  |  |  | N/A | Data | $ Currency |  | TC | 2 | A1 | F
F0000000 | XXX |  | 06 | level 6 | TP | TEMPLATE | GN | General Model | 07 | PDF | [7 empty] | TN | 1 | A3 | STA1-A
F0000000 | XXX |  | 07 | level 7 | RP | REPORT | ME | Mechanical | 08 | RVT | [7 empty] | TS | Z |  | STA1-B
F0000000 | XXX |  | 08 | level 8 | EX | EXCHANGE | NV | Environmental | 09 | WEB | [7 empty] | AC | U |  | STA1-C
F0000000 | XXX |  | 09 | level 9 | ES | ESTIMATION | PL | Plumbing | 10 | RCP | [7 empty] | AN | G |  | STA1-D
F0000000 | XXX |  | 10 | level 10 | PR | PRESENTATION | RS | Resilience and Sustainable Design | 11 | [8 empty] | AS |  |  | STA2-A
F0000000 | XXX |  | 11 | level 11 | SU | SURVEY | SM | Site Model | 12 | [8 empty] | BC |  |  | STA2-B
F0000000 | XXX |  | 12 | level 12 |  |  | ST | Structural | 13 | [8 empty] | BN |  |  | STA2-C
F0000000 | XXX |  | 13 | level 13 |  |  | TR | Traffic | 14 | [8 empty] | BS |  |  | STA2-D
F0000000 | XXX |  | 14 | level 14 |  |  | VT | Vertical Transportation | 15 | [8 empty] | CC |  |  | G40
[18 empty] | CN |  |  | G41
[18 empty] | CS |  |  | G42
[18 empty] | DC |  |  | G43
[18 empty] | DN |  |  | G44
[18 empty] | DS |  |  | G45
[18 empty] | EC |  |  | ML34
[18 empty] | EN |  |  | AL16
[18 empty] | ES |  |  | FL8
EE
FC
FS
FE

## DOOR&ROOM
ATL ¦ Door TAGs
NAMING STRUCTURE | Zone | Level | Room | Door | Review Status
DOOR TAG
ME-4-D3-STA1-C | ME | 4 | D3 | STA1-C | ACEPTED
ME-5-D4-STA1-C | ME | 5 | D4 | STA1-C | ACEPTED
ME-6-D5-STA1-C | ME | 6 | D5 | STA1-C | ACEPTED
ME-7-D6-STA1-C | ME | 7 | D6 | STA1-C | ACEPTED
ME-8-D7-STA1-C | ME | 8 | D7 | STA1-C | ACEPTED
ME-9-D8-STA1-C | ME | 9 | D8 | STA1-C | ACEPTED
ME-10-D9-STA1-C | ME | 10 | D9 | STA1-C | ACEPTED
ME-11-D10-STA1-C | ME | 11 | D10 | STA1-C | ACEPTED
ME-12-D11-STA1-C | ME | 12 | D11 | STA1-C | ACEPTED
ME-13-D12-STA1-C | ME | 13 | D12 | STA1-C | ACEPTED
NAMING STRUCTURE | Zone | Level | Room | Door | Review Status
ROOM NAME
ME-4-D3-STA1-C | ME | 4 | D3 | STA1-C | ACEPTED

## MEAM
ATL ¦ Model Element Authoring Matrix (MEAM)
The MEAM defines element ownership, modeling responsibility, and Level of Development (LOD) targets by discipline and project phase. It ensures clarity, prevents duplication of modeling effort, and supports efficient coordination across all trades involved in the ATL Airport expansion project.
Model Element | Discipline Responsible | SD | DD | CD | LOD Notes
Architectural Walls | Architecture | 100 | 200 | 350 | Modeled to accurate location and thickness by CD
Structural Columns | Structural | 100 | 300 | 350 | Coordination with slab openings and finishes
Ductwork (Main Runs) | Mechanical (HVAC) | — | 200 | 350 | Includes fittings, insulation in CD
Electrical Panels | Electrical | — | 200 | 350 | Coordinate with architectural rooms
Plumbing Fixtures | Plumbing | — | 200 | 350 | With rough-in and clearance zones
Doors and Hardware | Architecture | 100 | 300 | 350 | Schedule and parameters populated in DD
Fire Protection Heads | Fire Protection | — | 200 | 300 | Verify with ceiling heights and lighting
Ceilings | Architecture | — | 200 | 300 | Includes all grid layout and types
Lighting Fixtures | Electrical | — | 200 | 300 | Coordinated with ceiling grid and ducts
Conveying Systems | Specialty (BHS, Elevators) | — | 100 | 300 | Generic placeholders in DD, specific families in CD